## Project Plan
📋 1-PAGE PROJECT PLAN
Project: | My Project Name | Sponsor: |  | Version: | v1.0 | Date: | 2026-03-04 | Status: | On Track
🏁 MILESTONES ¦ Design Approved: 2025-05-15 ¦ Beta Live: 2025-06-01 ¦ Launch: 2025-06-30
May 2025
# | Task Name | Start | End | Duration (days) | Owner | Status | Priority | Deps | ▶ GANTT TIMELINE (weeks) |  | 09 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26
PHASE 1 — INITIATION
1.1 | Kickoff meeting & scope sign-off | 2025-05-01 | 2025-05-02 | 2 | Alice | Done | High
1.2 | Stakeholder alignment & RACI | 2025-05-02 | 2025-05-05 | 2 | Bob | Done | High | 1.1
1.3 | Risk register & assumptions log | 2025-05-05 | 2025-05-07 | 3 | Alice | In Progress | Medium | 1.2
PHASE 2 — PLANNING
2.1 | Requirements & acceptance criteria | 2025-05-07 | 2025-05-12 | 4 | Carol | In Progress | High | 1.2 | bar: 09 to 12
2.2 | Architecture & tech stack review | 2025-05-12 | 2025-05-16 | 5 | Dave | Not Started | High | 2.1 | bar: 12 to 16
2.3 | Resource & budget plan | 2025-05-14 | 2025-05-19 | 4 | Bob | Not Started | Medium | 2.1 | bar: 14 to 19
2.4 | Sprint planning & backlog grooming | 2025-05-19 | 2025-05-21 | 3 | Carol | Not Started | Medium | 2.2,2.3 | bar: 19 to 21
PHASE 3 — EXECUTION
3.1 | UI/UX design & prototype | 2025-05-21 | 2025-05-28 | 6 | Eve | Not Started | High | 2.2 | bar: 21 to 26
3.2 | Backend API development | 2025-05-21 | 2025-06-04 | 10 | Dave | Not Started | High | 2.2 | bar: 21 to 26
3.3 | Frontend integration | 2025-05-28 | 2025-06-09 | 9 | Frank | Not Started | High | 3.1,3.2
3.4 | QA & UAT testing | 2025-06-09 | 2025-06-18 | 7 | Eve | Not Started | High | 3.3
3.5 | Security & performance review | 2025-06-16 | 2025-06-20 | 5 | Dave | Blocked | High | 3.3
3.6 | Documentation & help articles | 2025-06-09 | 2025-06-23 | 10 | Carol | Not Started | Low | 3.3
PHASE 4 — LAUNCH & CLOSURE
4.1 | Staging deployment & smoke tests | 2025-06-20 | 2025-06-23 | 4 | Frank | Not Started | High | 3.4,3.5
4.2 | Production launch | 2025-06-28 | 2025-06-30 | 3 | Alice | Not Started | High | 4.1
4.3 | Post-launch monitoring & retro | 2025-06-30 | 2025-07-05 | 4 | Bob | Not Started | Medium | 4.2
STATUS SUMMARY
✅ Done: 2 |  | 🔄 In Progress: 2 |  | 🚫 Blocked: 1 |  | ⬜ Not Started: 8

## Legend & Instructions
LEGEND & FIELD GUIDE
STATUS VALUES
Not Started | Planned but work has not begun
In Progress | Actively being worked on
Blocked | Waiting on a dependency or decision
Done | Completed and reviewed
FIELD REFERENCE
Start / End | Task kickoff and finish date (YYYY-MM-DD)
Duration | Working days (integer). Tip: =NETWORKDAYS(Start, End)
Owner | Single accountable person (name or @handle)
Deps | Comma-separated Task IDs the task depends on (e.g. 1.2, 2.1)
PRIORITY
High | Must-have; on critical path
Medium | Important but has some flex
Low | Nice-to-have; do if capacity allows
GANTT COLORS
■ Blue | Not Started
■ Amber | In Progress
■ Red | Blocked
■ Green | Done
QUICK TIPS
Print layout | Landscape, Fit to 1 page, Letter/A4, no gridlines
Freeze panes | Header row is frozen at row 5 — scroll freely
Filters | Use the dropdowns in row 5 to filter by Status/Owner
Add rows | Duplicate a task row, update ID and Dep references